|  | # Capacity Development Programme Management Office |
| --- | --- |

Guidelines on the Use of the Regular Programme of Technical Cooperation (RPTC)

- Purpose of the guidelines

- Background (Overview of the Regular Programme for Technical Cooperation)

- Planning and approval process

- Revision of RPTC activity proposals

- Inter-Regional Advisors

- RPTC activity reporting

- Annexes

  - RPTC Activity Proposal Template

  - RPTC Activity Report Template

  - DESA Guidelines on the Recruitment and Administration of Inter-Regional Advisors

  - RPTC Common Reporting Standards

  - RPTC Work Plan Template

- Purpose of the guidelines

The purpose of these guidelines is to assist DESA’s divisions in the programming of funds through the Regular Programme of Technical Cooperation (RPTC). They are intended for all staff working on programming and implementing RPTC activities as well as those hiring temporary assistance staff funded through RPTC.

- Background (Overview of the Regular Programme for Technical Cooperation)

- The Regular Programme of Technical Cooperation was established by the General Assembly in its resolution 58 (I) in 1946. The programme’s broad objective is to support and advance processes aimed at developing the capacity of Governments to formulate and implement policies for sustainable economic and social development. Some of the main characteristics of the programme are the sharing of experiences across countries and regions, South - South cooperation, the use of national expertise from the beneficiary countries to the extent possible and the building of knowledge networks to facilitate continued exchange and assistance and promote sustainability.

- The Programme allows a fast and flexible response to requests of Member States for short-term assistance to meet small-scale capacity development-related challenges. Because of its shorter-term nature in comparison to longer-term projects, RPTC allows for more agile programming and often plays a catalytic role leading to longer-term formulation of assistance such as on the development and implementation of national development strategies and programmes. It complements activities under other funding portfolios, including under the Regular Budget, the Development Account, or extra-budgetary resources.

- The defining requirement of the RPTC is that it must be demand driven, responding to expressed needs by Member States for capacity development support. It is important to keep a focus on country demand at the same time as implementing a strategic vision to ensure that activities are in line with DESA’s overall capacity development strategy and priorities. RPTC programming should therefore strike a balance between planning to deliver on the objectives of the sub-programme and being responsive to urgent needs.

- RPTC is funded with resources from the UN Regular Budget (Section 23) and is implemented by eleven UN Secretariat entities. Each entity prepares the budget for its part for consolidation by Department of Management Strategy, Policy, and Compliance (DMSPC) and consideration by the Secretary-General. The General Assembly approves the Programme’s budget. The heads of the implementing entities serve as Programme Managers for their respective organizations. For DESA, the Under-Secretary-General (USG) clears the proposed budget prior to submission to DMSPC. CDPMO analyzes and consolidates budget proposals by the DESA sub-programmes for consideration by the USG and, upon approval of the Budget by the GA, manages the programming of the RPTC funds allocated to DESA.  This includes re-allocating funds between divisions to ensure optimal utilization of the resources. Divisions are responsible for the implementation of programmed funds and reporting on the results achieved.

# A key feature of RPTC is the availability of General Temporary Assistance (GTA) funds earmarked for recruitment of short-term Inter-Regional Advisors (IRAs) , as well as support staff at the general service level. IRAs are specialists in both capacity development and in the substantive area of the sub-programme. They are DESA’s technical and policy advisory arm to Member States by translating and contextualizing the department’s policy directions and normative recommendations to the national and local levels, thereby facilitating country-level access to DESAs expertise.

# Besides funding the IRAs, RPTC is used for small-scale capacity development activities, like training, workshops, and advisory services.

# Training and Workshops are undertaken in response to an identified capacity gap in one or more countries, and upon request by Member States. Inter-regional advisers, staff and/or consultants may lead and participate in seminars and workshops by developing training modules, facilitating discussions, and providing hands-on training. Seminars and workshops are held at the subnational, national, regional or global level.

# Advisory Services respond to requests from Governments for advice on policy related issues, to provide specific advice on sectoral matters relevant to their development strategies and programmes and to assist governments in the formulation and evaluation of programmes leading to the enhancement of national programmes. In-person advice may not always be necessary, as DESA supports the building of networks and can sometimes respond by following-up on queries electronically.

- RPTC can also be used to fund activities that pilot innovative tools or approaches. In these cases, activities are more experimental in nature aiming at scoping out useful next steps and further progress on respective issues. These activities generate important insights about assumptions and how to address identified needs.

# Strong backing by the UN Resident Coordinator indicates a good potential for cooperation with the UN country team and increases the chances of sustainability.

- Planning and approval process

- Divisions will be requested to prepare Programme Budgets for the RPTC every year. This preparation coincides with the Programme Budget preparation for the Regular Budget, usually one year in advance of the actual budget period.

- While many country interventions are programmed in the first quarter of the budget period, some activities are established in a phased manner throughout the budget period to allow for both optimal utilization of resources and for response to urgent requests from Member States in relation to unexpected circumstances. Divisions are required to submit a work plan (Annex 5) before the calendar year starts, by identifying indicative and emerging country needs. By June of each year, the entire RPTC budget should be fully programmed.

- When planning a response to a request for assistance or other demand, a division should assess whether it can provide support by going through the following questions:

# Is the request in line with the divisional mandates and the objectives of the department/division?

# Is the beneficiary country a developing country(ies), particularly LDCs, LLDCs and SIDS?

# Are there adequate financial and human resources available?

# Is there an opportunity to contribute to the desired development outcomes in addressing the need of the beneficiary?

- Demand includes:

        - direct country requests, which are defined as requests for DESA to provide capacity development assistance to a specific Member State that are communicated to DESA by the Government, Resident Coordinator’s Office (RCO), or another UN entity or intergovernmental organization;

        - needs identified through processes such as the Voluntary National Reviews (VNRs), Common Country Assessments (CCAs), or more specific technical assessments on different themes;

        - mandates from intergovernmental bodies.

- RPTC will give priority to funding activities that respond to direct country requests, all of which need to be entered in DESA’s capacity development request log. A direct country request is not, however, a precondition for RPTC funding, and DESA may fund RPTC activities that respond to other types of demand as listed in the previous paragraph.

- Proposals for funding of individual activities should be submitted to CDPMO for approval in the form of an RPTC Activity Proposal (see Annex 1). CDPMO either clears the RPTC Activity Proposal or requests the submitting division to provide additional documentation or undertake additional revisions to improve the proposal. RPTC can also cover the cost of travel to undertake advisory or technical assistance missions, or a consultancy which does not form part of a broader group of activities. In either of the cases please fill out only the parts of Annex 1 necessary to generate the cost assignment for implementation.

- CDPMO will review proposed RPTC activities vis-à-vis four general criteria:

- Activities should be responsive primarily to the demand of developing countries and be of a short-term nature (i.e., conceived and implemented within less than one calendar year); longer-term initiatives that require a phased approach and that build on knowledge and skills acquired through previous interventions may continue, pending the mobilization of external resources;

- Activities should fall within the priority areas of DESA as mandated by its governing bodies, and fall within its role in normative and analytical functions relating to the activities;

- Activities should build capacity in developing countries, including for meeting treaty and related normative obligations, and, through the sharing of experience gained at the country level, enrich the normative and analytical functions of the implementing entity for the benefit of all Member States;

- Activities that aid in the preparation of specialized components of a country’s development strategy or that help to prepare requests for larger-scale funding from other sources are encouraged. RPTC activities often play a catalytic role leading to longer-term assistance such as on the development and implementation of national development strategies and programmes, and complement activities under other funding portfolios, including under the Regular Budget, the Development Account, or extra-budgetary resources.

- CDPMO will also consider the division’s performance record regarding the implementation of ongoing and past projects and activities as well as its human resources capacities.

- The activities and the level of the budget should feasibly support the achievement of intended results. The budget should be used effectively for activities that have clearly identified capacity development results. RPTC does not fund travel to conferences/meetings/events that are in line with normative or inter-governmental activities.

- Considering an integrated approach in response to multi-dimensional capacity development needs of countries in pursuit of sustainable development, two or more divisions can develop a joint proposal with a coherent work plan, using the same template. Since the coordination and management arrangements must be specified in the proposal, a lead or coordinating division should be identified. The director of the lead division should sign off on the approval, in consultation with participating divisions and CDPMO will work with divisions on the budgetary arrangements.

- Whenever possible, and especially for countries that are not least developed countries (LDCs), activities should be undertaken on a cost-sharing basis, including through provision of in-kind contribution such as venues or funding of national participants, to ensure buy-in and ownership of Member States’ and the country team.

- Revision of RPTC activity proposals

# If divisions wish to make changes to the originally approved proposal approved by CDPMO, divisions will submit requests for change in writing to CDPMO for consideration. This would happen either formally through an amendment to the proposal or informally through an e-mail to CDPMO, depending on the following considerations

# Changes in the budget – if the budget increase is less than 10% of the budget or $10,000 (whichever is greater), then CDPMO will make the necessary changes without a formal request from the respective divisions. If, however, the increase is more than 10% of the budget or $10,000, whichever is greater, divisions must submit a revised proposal outlining: 1) why the activities could not be implemented as originally intended; 2) what has been achieved so far; 3) how the change will affect implementation; 4) the revised budget;

# Changes in the objectives and/or strategy – a new proposal must be submitted;

# Changes in timing and duration – a formal request is not required if the change is within three months of the original submission, but CDPMO should be notified;

# Changes in implementation arrangements, e.g., change of venue – a formal request is not required, but CDPMO should be notified.

- Inter-Regional Advisors

# As there are no established posts under RPTC, GTA funds are used for contracting Inter-Regional Advisors in response to requests from Governments for advisory and technical support services. IRAs are recruited to provide high level technical expertise; to facilitate the transfer of knowledge from global entities to governments on policy-related issues and strategies; and to assist in the formulation, assessment and/or evaluation of the national policies, strategies, programmes, and projects upon the request of Member States.

# IRAs operate as a unique interface between the inter-governmental policy making and DESA’s analytical work at headquarters, and the operational activities both at regional and country levels. IRAs facilitate access to the tools, resources, and expertise of the Department, acting as knowledge brokers.

# IRAs are expected to be fully integrated into their divisional Sub-Programme, implementing activities funded under RPTC, DA and other XB funding sources. IRAs should not be the primary project managers for projects that exceed 1 year. The recruitment and administration of IRAs is covered in a separate guidance (Annex 3).

# Because of limited funds available under RPTC to support IRA positions, the use of these positions must be optimized to deliver DESA’s mandates effectively. The Office of the Under-Secretary-General, with the support of CDPMO and the Capacity Development Steering Committee, ensures the optimal distribution of IRA positions within the Department. For this purpose, the Capacity Development Steering Committee reviews the trends and programme priorities for capacity development work within the Department and across Sub-Programmes to assess needs and resources, including the assignment of IRAs.

# The Steering Committee undertakes the following periodically:

# Review of the programme priorities towards determining or confirming the types of expertise required to support departmental and sub-programme priorities;

# Review and update the Generic Job Profiles (GJPs) of IRAs when required.; and

# The Departmental Panel will advise the Under-Secretary-General on the extension of IRA contracts.

- RPTC activity reporting

- Divisions undertaking RPTC activities need to submit RPTC Activity Reports (using the template in Annex 2) within two weeks of completion of the activity.

- A datasheet (Annex 2, page 1) should be completed separately for each RPTC activity, whereas the remainder of the RPTC Activity Report may be completed once to cover a group of related RPTC activities that were part of the same approved proposal.

- Divisions should keep a record on file of all training activities undertaken. This record, or activity report, should include a list of the training events, by topic, dates, venue, the number of participants by gender and by country of origin.

- Divisions should also maintain a record of evaluation forms completed by the participants attending the training workshop. The evaluation forms should indicate the extent to which the activity met their expectations and how it addressed their capacity needs. It is encouraged to use online forms for better analysis and statistics over time. You will find a customizable sample here.

- To facilitate the reporting on the results achieved in the context of the Programme Budget and the annual RPTC progress report, Divisions are encouraged to seek feedback on results achieved through their provided support. CDPMO will require such information (also see para 9) for reporting on the achieved results in the previous budget period.

- Such reporting will include information on

  - countries supported, disaggregated by SIDS, LDCs, LLDCs;

  - outreach conducted to ensure awareness on the work under RPTC is shared widely;

  - Types of support provided, including via virtual means, etc.

and be in line with the RPTC Common Reporting Standards (Annex 4), that were developed and approved by the 11 Implementing Entities in 2023, based on recommendations of ACABQ and the 5th Committee.

- Annexes

DESA’s Capacity Development strategy can be found on the Capacity Development Programme Development Office (CDPMO) website

# The Regular Programme of Technical Cooperation’ is distributed among eleven Implementing Entities:

# (Global)– including the Department of Economic and Social Affairs (DESA), the United Nations Conference on Trade and Development (UNCTAD), the United Nations Office on Drugs and Crime (UNODC), the Office of the United Nations High Commissioner for Human Rights (OHCHR), the United Nations Human Settlements Programme (UN-Habitat), and the Office for the Coordination of Humanitarian Affairs (OCHA);

(Regional)– including the Regional Commissions: Economic Commission for Africa (ECA), Economic Commission for Europe (ECE), Economic Commission for Latin America and the Caribbean (ECLAC), Economic and Social Commission for Asia and the Pacific (ESCAP), and the Economic and Social Commission for Western Asia (ESCWA).

IRA contracts are managed by CDPMO. CDPMO has issued Guidelines on the Recruitment and Administration of Interregional Advisers at Headquarters (Annex 3).